## Sheet1
Changes to be done | Number of resources | Estimated time (man days) | priority | Name | Status & Comments
KT | 1 week
Python training for new resources | 1 week
Inefficiency of the code.(Do design review and identify the improvement areas). | 1 | 1 | 1
Ethernet(connectivity) | 2 | 4 | 1 | Vishwas/
I2C(connectivity) | 2 | 4 | 1 | Vishwas/
SPI(connectivity) | 2 | 4 | 2 | Vishwas/
Emailing | 1 | 2 | 1
sms | 1 | 2 | 2
Quick run | 1 | 3 | 1
pdf report | 1 | 2 | 1
chat window |  |  | 3
Merging Automation and manual testing report.(consolidated report) | 1 | 2 | 1 | Ashwini
Data base code change for accessing data from single data base | 2 | 3 | 1
If existing test cases are in XLS, tool should be able to read it from XLS and store in data base. Currently all the test case details are stored in python. This has to ported to database. | 1 | 2 | 1 | ShriDutta
Creation of Database tables. | 1 | 2 and half | 1 | ShriDutta
Providing details logs against each test case for initial failure analysis. | 1 | 2 | 1
Providing library for logs (Providing standalone log library). | 1 | 2 | 1
Drag and drop features for Graphs | 1 |  | 2 |  | This feature is for chat window.
Drag and drop features for reports | 1 |  | 2 |  | This feature is for chat window.
Drag and drop features for history | 1 |  | 2 |  | This feature is for chat window.
Adding product plan (calendar view) | 1 |  | 3
Set up window (Team and product setup) | 1 |  | 1
Capability of tool being used as web application |  |  | 1
Testing application on OS environment | 1 |  | 1 | Pratap
Testing application in Linux environment both in user and Kernel space | 1 |  | 2 | Pratap
Director should be able to see the current run projects | 1 | 1 and half | 1
Delete button (Deleting the resent run ) | 1 | 1 and half | 1 | Srikanth | Abort button has the functionality to abort the run. GUI done. Functionalty remaining.
History of activity happened in the tool(Activity log) | 1 | 2 or 3
Linking test case discription to test report | 1 | 2
Signup should be restricted to Director/Admin. | 1 | 1 and half
Login Authentication should be done using django | 1 | 2
Login Password should be encrypted. | 1 | 1
Director Page should be dynamic; should be able to add more products. | 1 | 2
The values of Dropdown boxes are accessed through HTML pages; instead store it in Database and display it in UI. | 1 | 2 |  | Shridutt
Need to Discuss:If only one run of test is executed, then what the graph shows?
Need to Discuss:If first time test is to be run then what data should be displayed in Manager page?
Need to discuss: Representation of graphs as per Run/Release in Director page.
Remove "New Project" feature from Director Page. | 1 | 1 |  | Srikanth | GUI done. Functionalty remaining.
Datatype of "Expected Result" : need to be discussed
Create a "Settings" Page for Admin/Director. It should have options to add "Release no.", "Build no.", "Module", "Product","Category", "Communication mode". Admin should have option to move the "Test Execution" & "Actual Output" tables to backup. | 2 | 2 |  | Srikanth/ Shridutt
Instead of "Create" "Save" button should be there in form1.html page. | 1 | 1 or 2 |  | Srikanth | GUI done. Functionalty remaining.
Don’t move database tables to backup folder; instead keep updating table.Admin should have option to move the "Test Execution" & "Actual Output" tables to backup. | 2 | 2 |  | Srikanth/ Shridutt
"Modules" should have multiple choice option in form1.html page. | 1 | 4 to 5 hours |  | Srikanth | GUI done. Functionalty remaining.
Remove "All" option from "Category" in form1.html page. | 1 | 4 to 5 hours |  | Srikanth | GUI done. Functionalty remaining.
Add "Build" dropdown option in form1.html page. | 1 | 4 to 5 hours |  | Srikanth | GUI done. Functionalty remaining.
TestCases are from Code; it should be in Database table. | 1 | 1 |  | Shridutt
Add Scroll Bar for "TestCases" in form_submit.html page. | 1 | 1 hour |  | Srikanth | GUI done.
Filter Functionality should be available to filter the Testcases as per the modules in form1.html page. | 1 | 2 |  | Srikanth | GUI done. Functionalty remaining.
Session Management : For Signout. | 1 | 1
Remove "Cancel" on form_submit.html | 1 | 10 mins |  | Srikanth | Done.
Log files for each test case | 1 | 2 or 3
"Abort" Button on form2.html; it should show pop-up asking to abort the run; if aborted the Testcase Execution tables' data gets deleted but the submitted product info is saved. | 1 | 1 |  | Srikanth/ Shridutt | GUI done. Functionalty remaining.
"Submit_report" button on last_page.html; after clicking the button only the executed runs' data will be saved in Database. | 1 | 1 |  | Srikanth/ Shridutt | GUI done. Functionalty remaining.
Discard button:After Execution of Run/Build, if the user feels the run was not that properly executed or if there was some error in setup then the user may feel to discard the run. After clicking on this button, the user should be able to delete the data related to that run from the Database. | 1 | 1 |  | Srikanth/ Shridutt | GUI done. Functionalty remaining.
R & D of Python coding for Sever Client Programming | 2 | 2 |  | Snehali/
Documentation of Database Tables | 1 | 1 and half |  | Snehali | Including Meetings
Design of Code of complete Project